## Tabellenblatt1
identified | prob of occurrence | damage | mitigation strategy | person in charge | risk factor
neuronal network doesnt behave as expected | 25% | 100% | include more machine learning frameworks for usage but tensorflow | Steven & Marco | 25%
not enough time to get engaged with machine learning | 10% | 100% | start early enough with reading documentations | Steven & Marco | 10%
TDD takes to much time and work | 15% | 30% | priotize working solutions over tested but unworking code | Marco | 4.5%
untested funcionality doesnt work on first try | 50% | 5% | recode funtionality | Steven & Marco | 2.5%
project architecture becomes unclear | 10% | 15% | refactoring, could influence deadlines | Marco | 1.5%
private computer/server isn't strong enough to train the network | 30% | 15% | use computer from DHBW | Steven | 4.5%